## ESTIMATES
ID	Estimates	hours	Days

1)	Split the CSS Design Files into VOLT Files for Phalcon	8	1.3
2)	Database Redesign and optimiazation	12	2
3) + 4)	Metatags and Url Design	6	1
5)	FRONTEND functionality	30	5
6)	BACKEND	30	5

		86

		1,634.00	USD

		Price/h	19 USD

## FRONTEND - Mainpage
	FRONTEND

ID	MAIN PAGE

	Element	Description	Resulting Action / Further Information
#1	Quick-Search	-User can make a quick search, e.g. search "Post", Icon will be highlighted per Mouse-Over	1.) Search result page will be shown
		-In case that no town is selected above, PopUp needs to show up to select a town	> details will be deliverd within the project, these are minimal adjustments

	Element	Description	Resulting Action / Further Information
#2	Localize user	- Allows browser-based localisation (see small black icon next to logo)	1.) Position will be located

			2.) Postion will be shown in a map (see picture)

	Element	Description	Resulting Action / Further Information
#3	Search in Header	- Main function, appears on every single site of the website
		- Search shall not allow special charakters like *	> details will be deliverd within the project, these are minimal adjustments
		- Search shall allow autocomplete-function based on own database for the "what-field". / The "where-field" shall also allow autocomplete but based on google api	> please see also: http://www.oeffnungszeitenbuch.de/ - look at the / "was" field and the autocomplete me funktion
		- When user klicks on enter, serach also shall be conducted
		- If there is no place entered, the user shall be asked -May we use your location?- to / query the location by IP	> similar to #2
		- When any information is missing (what or where or both), popup under the search field shall be / displayed that the information is missing	> details will be deliverd within the project, these are minimal adjustments

	Element	Description	Resulting Action / Further Information
#4	Most wanted / new entries	- On the homepage there are 2 coloms with opening hours entries. "die neusten einträge" menas "new entries" and "die beliebtestens einträge" menas "most visited entries" > function for both shall be based on database

		- for each entry in general following info will be shown / name / Street / Distanz / Remaining time (x hours open)	> see www.who.das-alaborat.de

	Element	Description	Resulting Action / Further Information
#5	Blog Roll	- we have a wordpress blog (www.werhatoffen.de/blog), the latests 3 articels shall be displayed and / published automatically on the mainpage	Code already existing at werhatoffen.de

	Element	Description	Resulting Action / Further Information
#6	Add entry with opening hours	- this function is displayed on every site, compare layout
		to see the process please visit and http://werhatoffen.herokuapp.com/ klick / links below sitemap (Über uns, Häufige Fragen, Neue Öffnungszeiten eintragen, alle bundesländer, alle filialen	Please note the links below sitemap are only to demonstrate the process (this / is just the layout page without code. The process in our new version will be: user / klicks on "Öffnungszeiten eintragen" = "add new entrie" (see green button) and / he will then see the different steps of the entry process at once
			> details will be deliverd within the project, these are minimal adjustments

	Element	Description	Resulting Action / Further Information
#7	Advertisment	- Please make sure that we can replace advertisment code for Google Adsense easily
		- For home-site see www.who.das-elaborat and check where advertisment will appear

## FRONTEND - Detailpage
	FRONTEND

ID	Detailpage
example	http://who.das-elaborat.de/d/Deutsche-Post-Filiale-Hildener-Strasse-1-Erkrath-Hochdahl
	Element	Description	Resulting Action / Further Information
#1	Box1	- In the first Box (see picture, highlited in red) basic information of the store or cafe are made (based on database)					2
		- Small auto generated text is shown under the box					3
		- Advertisment will be shown (adsense)
		- user will have an opportunity to send an mail via contact formular when entry is wrong (see pic2 "Fehler melden" = Report Bug)

	Report Bug
#2	Edit entry	- user will have an opportunity to edit the information for an entry (openg hours, or details like phone, basically every info)
		> for that he will click on edit entry and he will see the following page (see pic 3) - a layer will show up where all information are summarized, / user shall be able to edit > the changes will then be submitted to us via email, we will need to approve the adjustments before we take any change / from a user live)	> we need to talk about that in detail
		- after having made some changes in the layer user can submit changes and he will see the info that his changes will be considerd by us

#3	Maps	Next to first box there shall be a google map with localisation, below there is a scpace for photos where we can import pics of the location
		Klicking on the first button lef below map will change map to google street view

#4	Box2	Bsic Information = opening hours are shown (inluding braking time)
		Below there is a shot auto generated text

#5	Box3	Here Google Maps API and Openstreet Maps API are used. Additonal info lile nearby streets are shown, nearby banks , busstations are shwon
		Under it there is a short autogenerated text

#6	Additional / Search results	Below the 3rd box there are additional results of the same category when available.	> we need to talk about that in detail , should be minimal effort
		Results are related to distance to the orginal distance (sorted !)

#7	Public holiday	In case that there is a public holiday (we will deliver a complete list oh public holiday), a message shall be shown on every detail page / "Pleaes note, today is public holiday, opening hours may differ".

## FRONTEND - Search
	FRONTEND

ID	Detailpage
example
	Element	Description	Resulting Action / Further Information
#1	listing of results		EXAMPLE: http://who.das-elaborat.de/s/M%C3%BCnchen?sub=148
		search results will be displayed
		as discussed on skype, the calculation of the distance of the entries is the crucial part
		each entry for search result will be listed based on distance
		for example: user searches for "bank" in "street" - than the street will be the reference point for the calculation of distance
		when user searches for "bank" in "city" than the city will be the referecne point for calulation (the middle point of the city)
		when user searches for "bank" in "cdistrict" than the district will be the referecne point for calulation (the middle point of the city)
		DATABASE NEEDS TO BE OPTIMISED FOR THAT CALCULATION!

#2	map	for each search result a map is shown as in the example (see right)
		mouse-over effect needs to be considerd: mouse is over one specific entry and the map icon is than highlighted (green)
		compare:
		http://who.das-elaborat.de/s/M%C3%BCnchen?sub=148

#3	BredCrumb Nvigation

## FRONTEND city,district
	FRONTEND

ID	Detailpage
example
	Element	Description	Resulting Action / Further Information
#1	City pages	More or less the same structe as main site - on the left side districts are shown from each city
		> search header, quick search, top entries and newest entries are displayed as on main site
		http://who.das-elaborat.de/c/Hamburg

#2	Listing page for all cities	listing off all states and cities

## Backend
	Description	Info 1	Info 2	Info 3	Info 4	Info 5	Comments

User-Administration	Add new Admins/Users	3 possibilities: admin, manager, user	admin=owners+you, manager = co-workers/interns, users = from outside
Website Offline	Maintanance possibility
Cache	Possibility to clear the cache
Entries	Entry management	The following functions should be included: Show all entries with possibility to edit them. possibility to get longitude + latitude for a given entry (again)	Functions: edit (all infos), delete, add, mark as "permanently closed", approval of edited entries / new entries, . Also please add a filter/search possibility to find the desired entry more quickly + Bulk Edit/Delete/Approve (Pictures) possibility / common filters should be displayed: all entries, edited entries, new entries for quick search	ideally this interface can be reached from outside so if we have interns they don't need to have a login to backend.	If users make entries or edit entries the system should give us an e-mail or show that in the interface... new entries can be modified / approved... for edited entries it should be visible which information was edited.. again possibility to re-edit	if an entry is changed + also the url there should be a 301 redirection made by system so the old url is redirected to the new one.		BY DEFAULT NE ENTRIES SHOULD BE IN A SEPARATE TABLE and NOT VISIBLE. After approval they will added to the approved table. / ALL CHANGES SHOULD BE SAVED IN A SEPARATE TABLE TO BE ABLE TO SEE LATER WHICH ENTRIES HAVE BEEN CHANGED AND HOW/WHICH INFORMATION
Filters for Entries	filters for entries	following filters: / a) has opening times / does not have opening times / has incomplete opening times / b) Entries which have most views/clicks / c) entries where it was clicked that the opening times are not correct	d) standard filters of course are: / name, district, city, plz, street etc... all information that is available
Banner/Advertisement	Change of advertisement	a) change for whole site / b) change by category / c) change by district / d) change for a specific entry / e) change by city / etc...

Other things

## Database
Main Entitiy

Business	Internal ID	Name of business	Address	Contact	Opening Hours	Description	Pictures	Statistics	Chain
Internal ID	unique number
name of business	not unique
address	Street	Street No	Postcode	City	Disctrict
contact	phone	fax	website	e-mail
opening hours	open	closed	by phone	by appointment	unknown
open	day1 open	day1 closing time	day1 open	day1 closing time	<--- if chosen open than he can add 2 times (opening+closing)... if he clicks + he can add two more	<-- this counts for each week day so we have 7 days
Description	Custom Text	Free Parking	WIFI	disabled friendly
Pictures	Logo	Other Pictures	<--- need to be approved by us to be displayed
Statistics	count views

chain	chain name	businesses
	<-- each business can belong to 1 chain, but 1 chain can have several businesses

address information	country	state	county	city	district	postcode	street
state	each state can only belong to 1 country		each state can have several countys, cities, districts and postcodes
county		each county belongs to 1 state		each county can have several cities, districts, postcodes and streets
city	each city belongs to 1 country	each city belongs to 1 state	each city belongs to 1 county but does not need to belong to a county		each city can have many districts, postcodes and streets
district	each district belongs to 1 country	each district belongs to 1 state	each district belongs to 1 county, but does not need to belong to a county	each district belongs to 1 city		each district can have many postcodes	each district can have many streets
postcode	each postcode blongs to 1 country	each postcode belongs to 1 state	each postcode can belong to a county	each postcode can belong to several cities	each postcode can belong to several districts
street	each street can belong to different postcodes, districts and cities...
street with no	street with no belongs to 1 district, 1 city, 1 postcode

Additional info	phone no	only allow phone numbers to be typed in
	e-mail	only allow emails

## Important Features
	Info

	description	priority
Location Targeting	User has possibility to give us GPS information (Desktop, Tablet and Mobile)	1	see Frontend (mainpage)
Holidays / Bank Holidays	give short information on entries in cities / states which might be closed due to holidays	1	see Frontend (detailpage)
Businesses permanently closed	small information on screen for businesses that have been marked for permanently closed	1
Database Design	Instead of only doing a new database design we need a script that converts the old database into the new one... at least the entry page, because we have lots of entries that we have not uploaded yet and it will be easier to have a script for these entries	1
duplicate check	duplicate check with new entries, but also in the backend	1
social links	put social links into description so google can'T spider them, same for all e-mail addresses and disclaimer texts	1	OPTIONAL
user interface in backend	to come	3

## Meta Tags
Explanation	Startseite = Homepage, Kategorie = category, Stadt = city, Seite = site, Stadtteil = district, Suche = search detailseite = detailpage

Startseite			index, follow
Title	Öffnungszeiten schnell und einfach finden | werhatoffen.de
Description	Finde Öffnungszeiten in deiner Stadt. Hat die Bank noch offen, wann öffnet der Supermarkt und wie lange hat die Post noch geöffnet? Alle Antworten bei uns.
Keywords	Öffnungszeiten, Öffnungszeiten Hamburg, Öffnungszeiten Köln, Öffnungszeiten Berlin, Öffnungszeiten Post, Öffnungszeiten Sparkasse, Öffnungszeiten Apotheken, geöffnet, wie lange offen, hat noch offen

Kategorie Seite Übersicht			Index, Follow, noarchive
Title	Alle Öffnungszeiten Kategorien im Überblick | werhatoffen.de
Description	Alle Öffnungszeiten Kategorien übersichtlich dargestellt. Insgesamt XXXXXX Öffnungszeiten in XXX Kategorien bei werhatoffen.de	XXXXXX und XXX dynamisch
Keywords	Öffnungszeiten Kategorien, Öffnungszeiten Post, Öffnungszeiten Supermarkt, Öffnungszeiten Bank, Öffnungszeiten Übersicht

Kategorie Seite	z.B. Apotheke		Index, Follow, noarchive
Title	Apotheke bei werhatoffen.de	"Apotheke" und XXXXX ist dynamisch
Description	Apotheke bei werhatoffen.de - Insgesamt XXXXX Öffnungszeiten in der Kategorie Apotheke. Kostenlose Einträge für alle Firmen	"Apotheke" und XXXXX ist dynamisch
Keywords	Öffnungszeiten Apotheke, Öffnungszeiten Apotheke Hamburg, Öffnungszeiten Apotheke Berlin, Öffnungszeiten Apotheke Köln, wie lange hat Apotheke offen	Top 3 Städte jeweils nach Anzahl der Öffnungszeiten , Apotheke ist dynamisch

Kategorie Seite + Stadt	beispiel Apotheke in Hamburg		Index, Follow
Title	Apotheke in Hamburg bei werhatoffen.de	"Apotheke" und "Hamburg" dynamisch
Description	Apotheke Hamburg bei werhatoffen.de - Insgesamt XXXXX Öffnungszeiten in der Kategorie Apotheke. Kostenlose Einträge für alle Firmen	Apotheke + Hamburg dynamisch (Kategorie + Stadt)
Keywords	Apotheke Hamburg, Apotheke Öffungszeiten Hamburg, wie lange hat Apotheke in Hamburg geöffnet,	Apotheke dynamisch

Stadt Seite	beispiel Hamburg		Index, Follow
Title	Öffnungszeiten von Hamburg bei werhatoffen.de
Description	Öffnungszeiten für Hamburg. werhatoffen.de bietet in Hamburg eine umfassende Suche nach Öffnungszeiten in allen Kategorien. Kostenlose Einträge für alle Firmen.
Keywords	Öffnungszeiten Hamburg, Ladenöffnungszeiten Hamburg, wer hat offen in Hamburg

Stadtteil Seite	beispiel Hamburg Niendorf		Index, Follow
Title	Öffnungszeiten von Hamburg Niendorf bei werhatoffen.de		Stadt + Stadtteil dynamisch
Description	Öffnungszeiten für Hamburg Niendorf. werhatoffen.de bietet in Hamburg Niendorf eine umfassende Suche nach Öffnungszeiten in allen Kategorien. Kostenlose Einträge für alle Firmen.
Keywords	Öffnungszeiten Hamburg Niendorf, Ladenöffnungszeiten Hamburg Niendorf, wer hat offen in Hamburg Niendorf

Suche	Beispiel "Restaurant" in "Berlin"		NoIndex, Follow
Title	Öffnungszeiten Suche für Restaurant in Berlin
Description	Alle Öffnungszeiten für Restaurant Berlin
Keywords	Öffnungszeiten Restaurant Berlin

Detailseite	Dr. Müller in Hauptstraße 16, 14044 Berlin
Title	Öffnungszeiten Dr. Müller Hauptstraße 16, 14044 Berlin | werhatoffen.de
Description	Öffnungszeiten von Dr. Müller in Hauptstraße 38, 10244 Berlin Mitte mit Adresse, Telefonnummer, Haltestellen und interaktiver Karte.
Keywords	Öffnungszeiten Dr. Müller Berlin, Öffnungszeiten Berlin, Kategorie, Subkategorie, geöffnet, Öffnungszeiten Hauptstraße 38, Tags (sofern vorhanden)	Dr. Müller Berlin, Kategorie, subkategorie, Hauptstraße 38, Tags sind dynamisch	Show a maximum of three tags

## URL rules
Seite	URL	Beispiel	Anmerkung	Index / Noindex
Startseite	www.werhatoffen.de			Index

Content-Seite Bundeslandübersicht	www.werhatoffen.de/bundeslaender	Alle Bundesländer		Index
Content-Seite Bundesland	www.werhatoffen.de/bayern	Bayern		Index
Content-Seite Stadt	www.werhatoffen.de/muenchen	München		Index
Content-Seite Stadtteil	www.werhatoffen.de/muenchen/mitte	München Mitte		Index
Content-Seite PLZ	www.werhatoffen.de/muenchen/89000	89000	If PLZ belongs to several different cities than show it with each city it belongs to	Index
Content Seite Straße	www.werhatoffen.de/muenchen/maximilianstrasse	Maximilianstraße		Index
Content Seite Kategorie	www.werhatoffen.de/hauptkategorie/unterkategorie			Index
Content Seite Filialen Übersicht	www.werhatoffen.de/filialen		alle filialen (all chains)	Index
Content Seite Filiale	www.werhatoffen.de/filialen/rewe	Rewe		Index

Suchseite	www.werhatoffen.de/s/		Search Site with Filters (will come soon)	Index
Suchseite Beispie	www.werhatoffen.de/s/muenchen/restaurant	Restaurant, München		NoIndex
Suchseite Alle Öffnungszeiten	www.werhatoffen.de/hamburg/	Alle Öffnungszeiten in Hamburg --> nur Ort eingegeben	if he only puts in the city with no search keyword he will get to the city page

Blog	www.werhatoffen.de/news		for the blog	Index
Presse	www.werhatoffen.de/presse		for press work	Index
Impressum	www.werhatoffen.de/impressum			NoIndex
Häufigste Fragen (FAQ)	www.werhatoffen.de/haeufigste-fragen			Index
Neue Öffnungszeiten Eintragen	www.werhatoffen.de/neue-oeffnungszeiten			Index

Öffnungszeiten-Seite	www.werhatoffen.de/o/laden-ort-strasse			Index
Öffnungszeiten Beispiel	www.werhatoffen.de/o/aldi-nord-hamburg-ekhofstrasse-37	Aldi Nord Hamburg Ekhofstraße 37	important don't show any ä,ü,ö spaces etc... also everything with small leters	Index